# Enhanced Monitoring Plan: To-Dos, Dependencies, and Trigger Map

This plan organizes the work needed to detect the threat actor on the customer network and automatically collect the malware they use. It covers the trigger and action map, workstreams with dependencies, the critical path, and open questions that could block progress.

# Trigger and Action Map

| Tier | Trigger | Detected in | Automated action | Notifications |
| --- | --- | --- | --- | --- |
| Critical | Manual trigger (analyst-initiated, per host) | Watcher VM | VMware snapshot of affected server | Watcher → Splunk HEC → Slack |
| Critical | Suspicious DLL load (defined IOA) | CrowdStrike | VMware snapshot of affected server | Watcher → Splunk HEC → Slack |
| Critical | cs_cookie length matching TA C2 pattern | IIS logs (Splunk or Falcon NG-SIEM, TBD) | VMware snapshot of affected server | Watcher → Splunk HEC → Slack |
| High | URL watchlist hit | IIS logs / CrowdStrike (source TBD) | Fusion SOAR: process dump of IIS (w3wp) / SharePoint | Impacted host → HEC (start/finish) → Slack |
| High | TA IP watchlist hit | CrowdStrike IOC | Fusion SOAR: process dump of IIS (w3wp) / SharePoint | Impacted host → HEC (start/finish) → Slack |
| Low | Low-confidence watchlist | CrowdStrike / Splunk | None, alert only | Slack |
| New | Recent CVE logic | CrowdStrike + Splunk | Tier assigned per CVE | Per assigned tier |

# To-Dos by Workstream

## A. Foundation (no dependencies, start now)

- A1. Create Splunk HEC tokens and a dedicated index (e.g., ir_automation). Use separate tokens for SOAR/endpoints and for the Watcher so a token exposed on a compromised host can be revoked without breaking anything else.

- A2. Define one event schema for all status messages: workflow_id, tier, trigger_type, hostname, aid, status (triggered/started/completed/failed), artifact (dump path, snapshot name, hash), timestamp. Every workflow sends the same fields, so Splunk alerts stay simple.

- A3. Confirm the network paths: monitored servers → HEC (8088), Watcher → vCenter/ESXi (443), Watcher → CrowdStrike API cloud, Watcher → HEC.

- A4. Confirm IIS W3C logging includes the cs(Cookie) field on every monitored site. It isn't enabled by default. Also confirm the logs are being ingested wherever the cookie logic will run.

- A5. Create the Slack channel and webhook for Splunk alert actions.

## B. CrowdStrike Alert Visibility (depends on A1, A2)

- B1. Add a first step to each Fusion workflow that posts "alert triggered" with the alert details to HEC.

- B2. Add workflow started, completed, and failed events to HEC, including a failure branch so broken runs are visible.

- B3. (Recommended) Ingest CrowdStrike detections into Splunk directly through the Falcon Event Streams add-on. This gives an independent record, allows alerting when a detection fires but no workflow-start event follows, and is required for the Splunk DLL-load parity in E1.

## C. High-Confidence Process Dump Workflow (depends on A1–A3)

- C1. Load the TA IPs as CrowdStrike custom IOCs and confirm where the URL watchlist is evaluated (see Open Questions).

- C2. Build and test the RTR process dump script. Target w3wp.exe (all app pools) and SharePoint processes such as OWSTIMER.exe. Check disk space first, hash the dumps, and decide on retrieval: RTR get or an evidence share.

- C3. Add HEC POSTs from the impacted server at workflow start and finish, with the dump hash and size in the finish message.

- C4. Test end to end with a benign trigger on a test host.

## D. Watcher VM (blocked on D0, customer provisioning)

- D0. BLOCKER. The customer provisions the Watcher VM. Send them requirements now so it's built right the first time: OS, network access from A3, and a vCenter service account.

- D1. vCenter service account with least privilege: snapshot create plus read. Configure snapshots to include memory (the .vmem is the best malware capture) and turn off quiescing.

- D2. Build a host mapping table from CrowdStrike AID/hostname to the vCenter VM object.

- D3. Create a CrowdStrike API client (alerts/detections read, hosts read, event streams). The Watcher should pull from CrowdStrike via streaming or polling; pushing from Falcon cloud to an on-prem box would require inbound exposure.

- D4. Snapshot service logic: per-host cooldown and deduplication, concurrency limit, datastore capacity check, and an offload/consolidation procedure. A leftover snapshot will grow and hurt production.

- D5. HEC notifications for snapshot requested, completed, and failed, including the snapshot name and ID (depends on A1, A2).

- D6a. DLL load trigger: write the custom IOA in CrowdStrike (e.g., unsigned or unusual-path DLL loaded into w3wp), set it to critical, and have the Watcher filter on that rule (depends on D3).

- D6b. Cookie length trigger. If the logic runs in Splunk, a Splunk alert webhook calls the Watcher, which is on-prem to on-prem and simpler. IIS logs are buffered, so expect some delay between the request and the snapshot (depends on A4, D0).

- D6c. Manual trigger: a simple CLI or web form that takes a hostname, logs the analyst's name, and sends a HEC event.

- D7. Test each trigger end to end with benign test cases.

## E. Splunk Parity and Slack (depends on A1, A4, A5; DLL rule also needs B3)

- E1. Recreate every trigger above as a Splunk correlation search, tagged by tier.

- E2. Add a Slack alert action for each search, with the tier, host, and trigger in the message.

- E3. Add health alerts: workflow started but not completed within X minutes, a CrowdStrike alert with no workflow-start event, and a missing Watcher heartbeat.

## F. Recent CVE Logic (feeds C, D, E)

- F1. Inventory recent CVEs for the exposed stack (IIS, on-prem SharePoint, .NET) from CISA KEV and MSRC. The 2025 SharePoint "ToolShell" chain (CVE-2025-53770/53771) is a good model: web shell drops in LAYOUTS and machine key theft.

- F2. Turn each CVE into detection logic and assign it a tier.

- F3. Deploy the logic to CrowdStrike (IOCs/IOAs) and Splunk.

- F4. Set a recurring review cadence.

# Critical Path

A1 and A2 unblock almost everything (B, C3, D5, E), so do them first. B and C can finish entirely while waiting on the customer. D0 is the only external blocker; everything else in D waits on it. The cookie-length trigger has two dependencies, A4 and the decision on where the logic runs, so settle that early.

# Open Questions and Gaps

- Where does the cookie-length logic run? CrowdStrike only sees IIS logs if they're shipped into NG-SIEM/LogScale. If they're only in Splunk, Splunk has to call the Watcher.

- Where is the URL watchlist evaluated? Inbound URL paths hit on the server show up in IIS logs, not standard Falcon endpoint telemetry. The IP watchlist works natively.

- Manual "GUID" trigger. Assumed to mean an analyst-initiated trigger per host. If it's a canary GUID/token being hit, that changes where the detection lives.

- Should critical triggers also run the process dump? A memory-inclusive snapshot mostly covers it, but it's worth deciding explicitly.

- OPSEC. A HEC token and scripts on a host the TA may control can be seen by them. Use a scoped, write-only token that can be rotated, or relay status through the SOAR instead. Process dumps can also tip off an attentive actor.